# CECODES Carbon Footprint Tool Weekly Delivery Plan

Companion to: CECODES Carbon Footprint Tool - Requirements.md (v1.1)
Purpose: A week-by-week plan so CECODES and the development team can track progress and give feedback every week.
Version: 1.0 (Draft)    Date: 2026-07-09

# How to Read This Plan

This plan is organized into phases. Every week ends with a visible deliverable for review during the weekly check-in.

It covers the full agreed scope: Excel parity, multi-company accounts, calculator, dashboard, admin factor library, and reports.

It does not prescribe implementation technologies.

The tool is built in Spanish (es-CO) from the first screen.

Timeline assumes a small team (1–2 developers). Larger teams can overlap phases while preserving order.

Two things from CECODES keep the plan on schedule:

Answers to Section 12 of the requirements (open decisions).

Confirmed, corrected emission-factor dataset.

# Project Timeline at a Glance

| Phase | Weeks | Focus | Weekly Deliverable |
| --- | --- | --- | --- |
| 0 | 1 | Sign-off & foundations | Agreed spec, factor list, project skeleton |
| 1 | 2–3 | Accounts & company setup | Register, log in, create company/facility/year |
| 2 | 3–4 | Emission-factor library | Admin manages factor library |
| 3 | 4–6 | Data-entry forms | Complete annual data entry |
| 4 | 6–8 | Calculation engine | Excel parity |
| 5 | 8–10 | Dashboard | Interactive visualizations |
| 6 | 10–11 | Reports | PDF + Excel/CSV |
| 7 | 11–12 | Hardening & launch | UAT and go-live |

## Phase 0 – Sign-off & Foundations (Week 1)

Collect Section 12 decisions and confirmed factor dataset.

Agree sample companies for parity testing.

Set up project skeleton and factor library structure.

Weekly Check-in Deliverable: Signed-off specification, confirmed factor list, running project shell.

## Phase 1 – Accounts & Company Setup (Weeks 2–3)

Registration, login, password reset.

Company User and CECODES Administrator roles.

Company → Facility → Reporting Year hierarchy.

Strict data isolation.

Weekly Check-in Deliverable: User registers, creates company/facility/year; admin approves/deactivates.

## Phase 2 – Emission-Factor Library (Weeks 3–4)

Load confirmed factors.

Admin can view/add/edit/deactivate with version history.

Yearly electricity grid factor.

Prepare version pinning.

Weekly Check-in Deliverable: Admin edits factor library with tracked history.

## Phase 3 – Data Entry Forms (Weeks 4–6)

Guided Scope → Category → Subcategory → Element flow.

Monthly Scope 2; annual Scopes 1 & 3.

Validation, save/resume, edit later.

Weekly Check-in Deliverable: Complete annual dataset entered and editable.

## Phase 4 – Calculation Engine (Weeks 6–8)

Per-gas calculations to CO₂e using GWP.

Special cases and unit conversions.

Roll-up totals and parity testing.

Weekly Check-in Deliverable: Tool matches Excel results for sample companies.

## Phase 5 – Dashboard & Visualizations (Weeks 8–10)

Totals, breakdowns, trends, filters, drill-downs.

Weekly Check-in Deliverable: Interactive dashboard.

## Phase 6 – Reports & Export (Weeks 10–11)

PDF report.

Excel/CSV export.

Weekly Check-in Deliverable: Downloadable reports.

## Phase 7 – Hardening, Acceptance & Launch (Weeks 11–12)

Spanish copy review.

Bug fixing, performance, access control.

UAT, deployment, hand-over.

Weekly Check-in Deliverable: CECODES-approved live tool.

# Recommended Weekly Check-in

Demo of the week's deliverable.

Comments & adjustments.

Decisions needed from CECODES.

Next week's goal and blockers.

# Timeline Risks

Late Section 12 answers or factor confirmations.

Pending Scope-3 methods.

Target (Meta) feature confirmation.

Larger parity-testing datasets.

Draft for discussion: Provide your team size and target launch date to convert these phases into calendar dates.